WEEK 3 TASK

Development Roadmap and
Implementation Strategy

Hypothetical Software Project: Library Management System

| Item | Details |
| --- | --- |
| Project Type | Web-based Library Management System |
| Development Approach | Agile / Scrum-inspired iterative development |
| Planned Duration | 12 weeks |
| Primary Users | Librarian and Member |
| Core Modules | Authentication, Books, Members, Issue/Return, Fines, Reports |
| Document Purpose | Development roadmap, implementation strategy, resource plan, risk plan, and testing/integration strategy |

Prepared as a self-contained academic project-planning document

# 1. Executive Summary

This document presents a detailed development roadmap and implementation strategy for a hypothetical Library Management System (LMS). The proposed system will digitize routine library operations such as maintaining book records, registering members, issuing and returning books, calculating overdue fines, and producing operational reports. The solution is designed for two primary user roles: Librarian and Member.

An Agile approach is selected because the project can be divided into small, testable increments and because requirements such as reporting, search behavior, fine rules, and user-interface details may evolve after early demonstrations. The plan uses six two-week sprints across a 12-week implementation window, with continuous testing and integration rather than leaving quality assurance until the end.

The roadmap prioritizes a usable minimum viable product (MVP): secure login, book and member management, issue/return workflows, fine calculation, and basic reports. Advanced improvements such as richer dashboards, accessibility refinements, performance tuning, and additional automation are treated as later increments.

## 1.1 Project Goals

Provide a centralized and consistent record of books, members, and transactions.

Reduce manual effort in issuing and returning books and calculating overdue fines.

Allow librarians to search and update inventory quickly.

Give members a clear view of their active loans and due dates.

Generate basic operational reports for inventory and circulation.

Deliver a maintainable system with documented testing, security controls, and deployment procedures.

## 1.2 Success Criteria

| Area | Target |
| --- | --- |
| Functional completeness | All MVP workflows operate end-to-end without critical defects. |
| Quality | Critical/high-severity defects are resolved before release; regression suite passes for release candidate. |
| Security | Role-based access is enforced and common web risks are addressed during design and testing. |
| Usability | A librarian can complete common book and circulation tasks without developer assistance. |
| Performance | Normal library operations respond within an agreed acceptable threshold under expected load. |
| Maintainability | Code is modular, documented, version-controlled, and supported by automated tests for critical logic. |

# 2. Project Baseline and Scope

## 2.1 Proposed System

The Library Management System is a role-based web application intended for a small-to-medium educational or community library. The librarian manages the catalog and circulation records, while members use the system to view available books and their own borrowing information.

## 2.2 In-Scope Features

| Module | Key Capabilities | Priority |
| --- | --- | --- |
| Authentication & Authorization | Login, logout, password handling, role-based permissions | Must-have |
| Book Management | Add, update, delete, search, availability status, category/author details | Must-have |
| Member Management | Register, update, search, deactivate members | Must-have |
| Issue / Return | Issue book, due date, return book, transaction history | Must-have |
| Fine Management | Calculate overdue fine, display outstanding amount, record settlement | Must-have |
| Reports | Inventory, active loans, overdue books, transaction summary | Should-have |
| Validation & Error Handling | Input validation, meaningful errors, duplicate prevention | Must-have |
| Audit / Logging | Important actions and failures recorded for troubleshooting | Should-have |

## 2.3 Out-of-Scope for Initial Release

Online payment gateway integration for fines.

Biometric or RFID hardware integration.

Native Android/iOS applications.

Complex multi-branch library synchronization.

Machine-learning-based recommendation features.

Integration with external national or commercial book catalogs.

## 2.4 Assumptions and Dependencies

A stable development environment, version-control repository, and relational database are available.

The library's basic fine rules and user roles can be agreed before the corresponding sprint begins.

Test data can be created without exposing real personal information.

Deployment infrastructure and credentials will be available before the release sprint.

Third-party libraries will be reviewed and version-pinned to reduce supply-chain risk.

# 3. Development Roadmap

The project is planned for 12 calendar weeks. The sequence deliberately overlaps development and testing: requirements and architecture are stabilized early, while every sprint ends with an integrated increment that can be demonstrated and evaluated.

| Phase | Weeks | Primary Outputs | Exit Gate |
| --- | --- | --- | --- |
| 1. Initiation & Planning | 1 | Scope, backlog, acceptance criteria, project plan | MVP backlog approved |
| 2. Requirements & UX/Architecture | 2 | Use cases, wireframes, architecture, data model | Design baseline approved |
| 3. Sprint 1 — Foundation | 3–4 | Project setup, authentication, base DB, navigation | Foundation increment tested |
| 4. Sprint 2 — Catalog & Members | 5–6 | Book and member management | CRUD workflows pass |
| 5. Sprint 3 — Circulation | 7–8 | Issue/return, due dates, transaction history | Core circulation works end-to-end |
| 6. Sprint 4 — Fines & Reports | 9–10 | Fine engine, reports, audit logging | Business rules validated |
| 7. System Hardening | 11 | Regression, security, performance, usability fixes | Release candidate accepted |
| 8. Deployment & Closure | 12 | Production deployment, documentation, handover | Release and sign-off |

## 3.1 Milestone Schedule

| Milestone | Planned Completion | Deliverable / Evidence | Owner |
| --- | --- | --- | --- |
| M1 — Project baseline | End of Week 1 | Approved scope, product backlog, Definition of Done | Product Owner / PM |
| M2 — Design baseline | End of Week 2 | Wireframes, architecture, ER model, API outline | Architect / UI / Dev |
| M3 — Foundation increment | End of Week 4 | Running app, authentication, DB connection | Development Team |
| M4 — Catalog increment | End of Week 6 | Book/member workflows | Development + QA |
| M5 — Circulation increment | End of Week 8 | Issue/return and transaction history | Development + QA |
| M6 — Business increment | End of Week 10 | Fines, reports, audit logging | Development + QA |
| M7 — Release candidate | End of Week 11 | Regression/security/performance evidence | QA Lead |
| M8 — Production release | End of Week 12 | Deployed system, user/admin documentation | Release Owner |

# 4. Implementation Strategy

## 4.1 Methodology Selection

The recommended methodology is Agile with a Scrum-inspired cadence. The approach is suitable because the project has a clear overall objective but contains details that can be refined after users interact with working software. Agile principles emphasize early and continuous delivery of valuable software, frequent delivery of working software, collaboration between business and development participants, technical excellence, and regular reflection and adaptation.

The implementation will use two-week sprints. Each sprint begins with a planning session, proceeds through design/development/testing/integration activities, and ends with a review and retrospective. Work will be prioritized by business value and risk rather than by attempting to complete every module at once.

## 4.2 Scrum-Inspired Roles

| Role | Responsibilities |
| --- | --- |
| Product Owner | Prioritizes backlog, clarifies requirements, confirms acceptance criteria, accepts/rejects completed work. |
| Scrum Master / Project Coordinator | Facilitates planning, removes blockers, tracks risks, supports team process and retrospectives. |
| Frontend Developer | Builds UI, client-side validation, navigation, responsive behavior, and frontend integration. |
| Backend Developer | Implements APIs, business logic, authorization, database operations, and error handling. |
| QA / Test Engineer | Creates test cases, executes functional/regression testing, verifies fixes, and maintains quality evidence. |
| DevOps / Release Support | Manages environments, CI/CD, deployment configuration, backups, and release checks. |

## 4.3 Sprint Cadence

| Activity | Timing | Purpose |
| --- | --- | --- |
| Sprint Planning | Start of sprint | Select backlog items and confirm sprint goal. |
| Daily Stand-up | Daily, 15 min | Synchronize progress, blockers, and next steps. |
| Backlog Refinement | Mid-sprint | Clarify upcoming stories and acceptance criteria. |
| Development + Testing | Throughout sprint | Build, integrate, test, review, and fix incrementally. |
| Sprint Review | End of sprint | Demonstrate working increment and gather feedback. |
| Retrospective | After review | Identify process improvements for the next sprint. |

## 4.4 Definition of Done

Acceptance criteria are satisfied and demonstrated.

Code is reviewed and merged into the main integration branch.

Unit and relevant integration tests pass.

No unresolved critical defect remains for the story.

Input validation and authorization are implemented where applicable.

Documentation or API notes are updated when behavior changes.

The feature works in the shared test environment.

# 5. Work Breakdown and Initial Implementation Steps

## 5.1 Product Backlog — Representative User Stories

| ID | User Story | Acceptance Criteria | Priority |
| --- | --- | --- | --- |
| US-01 | As a librarian, I want to log in securely so that only authorized staff can manage records. | Valid login works; invalid login rejected; role checked. | Must |
| US-02 | As a librarian, I want to add and edit books so that the catalog remains current. | Required fields validated; changes persist; duplicates handled. | Must |
| US-03 | As a librarian, I want to register members so that borrowing can be tracked. | Unique member ID; required fields; deactivate option. | Must |
| US-04 | As a member, I want to search books so that I can find available titles. | Search by title/author/category; availability shown. | Must |
| US-05 | As a librarian, I want to issue a book so that a loan is recorded with a due date. | Eligible member/book; transaction stored; availability updated. | Must |
| US-06 | As a librarian, I want to return a book so that inventory becomes available again. | Open loan closed; return date stored; fine evaluated. | Must |
| US-07 | As a librarian, I want automatic fine calculation so that overdue amounts are consistent. | Rule applied consistently; amount auditable. | Must |
| US-08 | As a librarian, I want reports so that I can monitor overdue books and circulation. | Reports filter correctly and show accurate totals. | Should |

## 5.2 Initial Technical Setup

Create the Git repository with protected main branch and documented branching strategy.

Create separate development, test, and production configuration profiles.

Initialize the web application and database connection.

Create the initial relational schema for users, books, members, loans, fines, and audit events.

Add environment-variable handling for secrets and database credentials.

Set up automated build/test checks for pull requests.

Create seed data for repeatable development and testing.

Create baseline API documentation and coding conventions.

## 5.3 Suggested Logical Architecture

A three-layer architecture is recommended: presentation layer, application/service layer, and data-access layer. The presentation layer handles user interaction; the service layer contains business rules such as eligibility and fine calculation; the data-access layer isolates database operations. This separation makes individual components easier to test and reduces coupling.

| Layer | Examples | Primary Quality Concern |
| --- | --- | --- |
| Presentation | Login page, catalog, member form, circulation screens | Usability, validation, accessibility |
| API / Service | Authentication, book service, loan service, fine service | Business correctness, authorization |
| Data | Users, books, members, loans, fines, audit tables | Integrity, consistency, backup |
| Cross-cutting | Logging, error handling, configuration, security | Observability, confidentiality, reliability |

# 6. Resource and Effort Estimation

The estimates below represent a realistic academic/project-team planning baseline rather than a fixed commitment. They should be recalibrated after the first sprint using actual velocity.

| Stage | Duration | Estimated Effort | Primary Resources |
| --- | --- | --- | --- |
| Planning & requirements | 1–2 weeks | 32 person-hours | PO/PM, developer, QA |
| UX & architecture | 1–2 weeks | 36 person-hours | UI, architect/dev, QA |
| Foundation & authentication | 2 weeks | 48 person-hours | Frontend, backend, QA |
| Books & members | 2 weeks | 56 person-hours | Frontend, backend, QA |
| Issue/return | 2 weeks | 60 person-hours | Frontend, backend, QA |
| Fines & reports | 2 weeks | 56 person-hours | Frontend, backend, QA |
| Hardening & release | 2 weeks | 48 person-hours | QA, dev, release support |
| Total baseline | 12 weeks | 336 person-hours | Cross-functional team |

## 6.1 Resource Assumptions

Core team: 1 product/project coordinator, 1 frontend developer, 1 backend developer, 1 QA/test engineer, and part-time deployment support.

Team members may cover more than one role in a small academic project.

Effort includes development and testing but excludes extended post-release support.

The assignment itself is expected to require approximately 30–35 hours of thorough planning, analysis, documentation, review, and refinement; this is separate from the 12-week software implementation estimate.

## 6.2 Effort Allocation by Work Type

| Work Type | Approx. Share | Purpose |
| --- | --- | --- |
| Requirements & analysis | 12% | Clarify workflows, acceptance criteria, constraints. |
| Design & architecture | 13% | UI, data model, APIs, security design. |
| Implementation | 38% | Frontend, backend, database, business rules. |
| Testing & defect fixing | 24% | Unit, integration, system, regression, security and usability checks. |
| Deployment & documentation | 8% | Release configuration, user/admin documentation. |
| Risk / contingency | 5% | Unplanned rework, dependency delays, defect spikes. |

# 7. Risk Assessment and Mitigation

Risk management is continuous rather than a one-time activity. Risks are reviewed during sprint planning and retrospectives. Priority is assigned using likelihood and impact, with mitigation actions identified before the risk becomes a blocker.

| Risk | Likelihood | Impact | Mitigation / Response | Owner |
| --- | --- | --- | --- | --- |
| Changing requirements | Medium | High | Maintain prioritized backlog; use acceptance criteria; defer non-MVP changes to later sprints. | PO/PM |
| Database/data-model changes | Medium | High | Review schema before implementation; use migrations and version control. | Backend |
| Integration conflicts | Medium | Medium | Small pull requests, frequent merges, CI checks, shared API contracts. | Tech Lead |
| Security vulnerabilities | Medium | High | Threat-aware design, authorization checks, dependency updates, security testing. | Backend/QA |
| Insufficient test coverage | Medium | High | Risk-based test design; automate critical workflows; regression suite before release. | QA |
| Third-party dependency failure | Low/Med | High | Pin versions, review dependencies, maintain replacement strategy, scan dependencies. | DevOps |
| Performance degradation | Low/Med | Medium | Define basic performance targets early; test representative queries and workflows. | Dev/QA |
| Deployment/configuration errors | Medium | High | Separate environments, configuration checklist, repeatable deployment scripts. | DevOps |
| Resource unavailability | Medium | Medium | Document critical knowledge; cross-train; prioritize MVP backlog. | PM |
| Poor user adoption | Low/Med | Medium | Prototype early, conduct usability feedback sessions, simplify common workflows. | PO/UI |

## 7.1 Risk Response Matrix

High likelihood + high impact: actively mitigate before the affected sprint begins.

Low likelihood + high impact: maintain contingency and monitoring.

High likelihood + low impact: reduce through process or automation.

Low likelihood + low impact: monitor without consuming disproportionate project effort.

# 8. Integration and Testing Plan

## 8.1 Testing Strategy

Testing is embedded throughout development. Each user story receives test design before or alongside implementation. The testing pyramid is used conceptually: many fast unit tests for business logic, a smaller set of integration/API tests, and a focused set of end-to-end tests for critical user journeys.

| Test Level | Scope | Examples | Timing |
| --- | --- | --- | --- |
| Unit Testing | Individual functions/classes/services | Fine calculation, validation, eligibility rules | Every feature |
| Integration Testing | Module/API/database interaction | Issue book → create loan → update availability | Every sprint |
| System / E2E | Complete workflows | Login → search → issue → return → report | Every release candidate |
| Regression Testing | Previously working behavior | Authentication, catalog, circulation, reports | Every sprint/release |
| Security Testing | Authorization and common application risks | Access control, injection, session handling | Each sprint + hardening |
| Performance Testing | Response time and basic load behavior | Search, reports, concurrent issue requests | Sprint 4 + hardening |
| Usability Testing | Task completion and clarity | Librarian completes issue/return workflow | Prototype + RC |
| Acceptance Testing | Business acceptance | MVP acceptance criteria and scenarios | Sprint reviews + final |

## 8.2 Module Integration Sequence

Integrate authentication with the user database and role checks.

Integrate book and member CRUD modules with validated database transactions.

Integrate circulation service with book availability and member eligibility.

Connect fine calculation to return processing and outstanding-fine records.

Integrate reports with transactional data using read-only/reporting queries where practical.

Add audit logging and centralized error handling across sensitive operations.

Run end-to-end regression against the integrated release candidate.

## 8.3 Critical End-to-End Test Scenarios

| Scenario | Expected Result |
| --- | --- |
| Valid librarian login | Librarian reaches authorized dashboard and restricted pages are accessible. |
| Invalid login | Access denied with safe error message; no sensitive information exposed. |
| Add new book | Book is stored and searchable; required fields are validated. |
| Issue available book | Loan created, due date assigned, book marked unavailable. |
| Issue unavailable book | Transaction rejected and user receives clear reason. |
| Return on time | Loan closes and no overdue fine is created. |
| Return overdue book | Loan closes and fine is calculated according to configured rule. |
| Unauthorized member access | Member cannot access librarian-only functions. |
| Generate overdue report | Report contains correct overdue records and totals. |
| Concurrent update | System preserves data integrity and does not create duplicate active loans. |

## 8.4 Defect Management Workflow

QA or reviewer records the defect with title, environment, steps to reproduce, expected result, actual result, severity, and evidence.

Developer triages the issue and links it to the relevant user story.

Fix is implemented in a branch and reviewed.

Automated and manual tests are executed to verify the fix.

Regression testing checks affected workflows.

Defect is closed only after evidence confirms the expected behavior.

# 9. Security and Quality-by-Design Controls

Because the system stores user and transaction information, security is treated as a design concern rather than a final-stage activity. The plan includes authentication, least-privilege authorization, input validation, secure configuration, logging, dependency management, and secure error handling.

Passwords must never be stored in plaintext; use a strong password-hashing mechanism provided by the chosen framework.

Authorization checks must occur on the server/API layer, not only in the user interface.

Use parameterized queries or ORM-safe mechanisms to reduce injection risk.

Validate and constrain user input at system boundaries.

Do not place credentials or secret keys in source control.

Use HTTPS in deployed environments and protect session/token handling.

Log security-relevant events without logging passwords or other sensitive secrets.

Review dependencies and keep supported versions; track known vulnerabilities.

Use backups and restore procedures appropriate to the importance of the database.

The security review will use the OWASP Top 10 as an awareness baseline. The current OWASP Top 10:2025 highlights risks including broken access control, security misconfiguration, software supply-chain failures, cryptographic failures, injection, insecure design, authentication failures, integrity failures, logging/alerting failures, and mishandling exceptional conditions.

# 10. Deployment and Release Strategy

## 10.1 Environment Strategy

| Environment | Purpose | Data Policy | Deployment Trigger |
| --- | --- | --- | --- |
| Development | Local feature development | Synthetic/local test data | Developer branch |
| Test / QA | Integration and formal testing | Synthetic controlled data | Merge to integration branch |
| Staging | Release-candidate validation | Anonymized/synthetic data | Release candidate |
| Production | Live library operations | Real operational data | Approved release |

## 10.2 Release Checklist

All release-scope acceptance criteria verified.

Critical and high-severity defects resolved or formally accepted.

Regression suite passes.

Database migration/back-up plan validated.

Production configuration and secrets verified.

Security checks completed.

Monitoring/logging enabled.

Rollback procedure documented.

User/admin documentation updated.

Release owner records final approval.

# 11. Metrics and Progress Tracking

| Metric | How It Is Used | Target / Interpretation |
| --- | --- | --- |
| Sprint velocity | Track completed story points over time | Use trend for planning; do not treat as a performance score. |
| Defect density | Observe defects relative to delivered functionality | Declining trend as release stabilizes. |
| Defect severity | Prioritize quality risks | No open critical defects at release. |
| Test pass rate | Assess release readiness | All critical-path tests pass. |
| Requirement coverage | Confirm stories have tests | 100% of must-have stories linked to acceptance tests. |
| Cycle time | Measure time from development start to completion | Reduce avoidable waiting and handoffs. |
| Build/CI status | Detect integration problems early | Main integration branch remains buildable. |

# 12. Week-by-Week Implementation Plan

| Week | Focus | Key Activities | Milestone |
| --- | --- | --- | --- |
| 1 | Planning | Scope, stakeholders, backlog, acceptance criteria, risks, repo | M1 |
| 2 | Design | Wireframes, architecture, ER model, API contracts, test strategy | M2 |
| 3 | Sprint 1 | Project setup, DB, authentication UI/API | Foundation in progress |
| 4 | Sprint 1 | Role checks, navigation, validation, unit/integration tests | M3 |
| 5 | Sprint 2 | Book CRUD, search, member CRUD | Catalog/member in progress |
| 6 | Sprint 2 | Availability, validation, regression tests | M4 |
| 7 | Sprint 3 | Issue workflow, eligibility, due dates | Circulation in progress |
| 8 | Sprint 3 | Return workflow, transaction history, integration tests | M5 |
| 9 | Sprint 4 | Fine calculation, outstanding fines, reports | Business increment in progress |
| 10 | Sprint 4 | Audit logging, report validation, regression | M6 |
| 11 | Hardening | Security, performance, usability, full regression, defect fixing | M7 |
| 12 | Release | Staging validation, deployment, documentation, handover | M8 |

# 13. Contingency and Change Management

The roadmap protects the MVP by maintaining a prioritized backlog. If the project falls behind, the first response is not to reduce testing quality; instead, lower-priority features such as advanced reports or cosmetic enhancements are deferred. Changes that affect data models or core security are assessed for technical impact before acceptance.

| Situation | Response |
| --- | --- |
| Sprint capacity lower than expected | Reduce sprint scope and preserve highest-value stories. |
| New requirement appears | Create backlog item, estimate impact, prioritize against existing work. |
| Critical defect discovered | Pause affected release work, fix, retest, and reassess milestone. |
| Dependency unavailable | Use approved version, alternative component, or temporary stub where safe. |
| Architecture issue discovered | Document trade-off, create technical task, fix before expanding dependent modules. |
| Release blocked | Use rollback/contingency plan and move unresolved noncritical work to next release. |

# 14. Final Evaluation and Acceptance Criteria

| Evaluation Dimension | Evidence Required |
| --- | --- |
| Logical sequencing | Roadmap shows dependencies from requirements through design, implementation, integration, testing and deployment. |
| Milestone precision | Each milestone has a planned week, deliverable, owner and exit gate. |
| Resource feasibility | Effort estimates identify roles and contingency. |
| Implementation feasibility | Agile cadence, backlog, Definition of Done, environments and release process are defined. |
| Testing completeness | Unit, integration, system, regression, security, performance, usability and acceptance testing are covered. |
| Risk clarity | Risks include likelihood, impact, mitigation and ownership. |
| Professional documentation | Consistent headings, tables, terminology, references and self-contained explanations. |

## 14.1 Release Acceptance Checklist

All Must-have user stories accepted.

All critical workflows tested end-to-end.

No open critical defect.

High-severity defects either resolved or formally accepted with documented rationale.

Security review completed.

Database backup and rollback approach verified.

User documentation delivered.

Stakeholder/Product Owner sign-off recorded.

# 15. Conclusion

The proposed roadmap provides a practical path from project initiation to production deployment for the Library Management System. Its main strength is incremental delivery: the team builds and validates a usable foundation first, then adds catalog, membership, circulation, fine, and reporting capabilities.

The implementation strategy balances delivery speed with quality. Agile planning provides flexibility, while Definition of Done, continuous integration, risk-based testing, security controls, and explicit release gates prevent flexibility from becoming uncontrolled scope change. The result is a feasible 12-week roadmap that can be adapted using actual sprint velocity without losing the project's core objectives.

# 16. Publicly Available References and Best-Practice Sources

Agile Manifesto — Principles Behind the Agile Manifesto
https://agilemanifesto.org/iso/en/principles.html
Used to inform iterative delivery, frequent working software, collaboration, technical excellence and continuous improvement.

The Scrum Guide — November 2020
https://scrumguides.org/scrum-guide.html
Used as the reference for Scrum concepts, events and empirical/iterative planning.

Scrum Guide — Official PDF
https://scrumguides.org/docs/scrumguide/v2020/2020-Scrum-Guide-US.pdf
Official Scrum Guide document used for methodology grounding.

ISTQB — Official Testing Knowledge
https://istqb.org/what-we-do/
Used to ground software-testing terminology and the importance of structured testing knowledge.

ISTQB Glossary
https://glossary.istqb.org/
Used as a public reference for standardized testing terminology such as acceptance testing and related concepts.

OWASP Top 10:2025
https://top10.owasp.org/2025/en/
Used as a security-awareness baseline for web application risks.

# Appendix A — Compact Traceability Matrix

| Requirement | Planned Module | Test Evidence | Release Gate |
| --- | --- | --- | --- |
| Secure access | Authentication/Authorization | Login + role-access tests | M3 |
| Book management | Book Service/UI | CRUD + validation tests | M4 |
| Member management | Member Service/UI | CRUD + authorization tests | M4 |
| Issue/return | Circulation Service | End-to-end loan scenarios | M5 |
| Fine calculation | Fine Service | Boundary and overdue tests | M6 |
| Reports | Reporting Module | Data accuracy tests | M6 |
| Security | Cross-cutting | Security checklist + targeted tests | M7 |
| Release readiness | Deployment | Regression + acceptance evidence | M8 |

# Appendix B — Definition of Key Terms

| Term | Meaning in This Project |
| --- | --- |
| MVP | Minimum Viable Product containing the essential library workflows. |
| Sprint | A fixed development cycle used to produce a usable increment. |
| Backlog | Prioritized list of product work, improvements, defects and technical tasks. |
| Acceptance Criteria | Conditions that a user story must satisfy to be accepted. |
| Regression Testing | Testing to confirm that existing functionality remains correct after changes. |
| Integration Testing | Testing interactions between modules, services, database and external components. |
| Release Candidate | Build considered sufficiently complete for final validation before production. |